## 1. Product Overview
Item | Description
Product Name | AURALIS
Product Vision/ Purpose | To create an AI tool that helps psychologists and doctors better understand and support patients through intelligent emotional insights
Business Goals / Key Success factors | To simplify therapy through AI-driven emotion analysis and smart notes.Success depends on accuracy,adoption,security and scalability.
Primary Stakeholders | Psychologists,Psychiatrists,Therapists and other Healthcare proffessionals.

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | Seamless session documentaion | US1 | As a psychologist, I want automatic audio to text transcription | Database,Androis/IOS device,microphone access,transcription model | Must Have |  | almost there | Tejasvi | not yet done | Vishal,Suchitra
E2 | Session summarization | US2 | As a therapist,I want auto-generated summaries so I can quickly review key from each session | AI summarizer(gemini) | Must have |  | Not yet | sudha | not yet done | Vishal
E3 | Doctor notes and review | US3 | As a therapist,I want to add,edit or verify my own notes after receiving the AI-generated summary |  | Must Have |  | Not yrt | tejasvi,sudha | not yet done | Vishal,Suchitra
E4 | Emotion and Keyword Detection | US4 | I want the dashboard to highlight and flag critical or alarming words | NLP | Must Have |  | Not yet | tejasvi,sudha | not yet done | Vishal
E5 | Authentication | US5 | Log in securely with verified credentials so that that only authorized users can access sensitive patient data and session details | Google OAuth 2.0 | Must Have |  | Not yet | Tejasvi | not yet done | Vishal,Suchitra
E6 | Dashboard | US6 | As a user, I want a main dashboard summarizing all my key matrics and stats in one view. | Database connectivity and optimize search algorthim | Should Have |  | Not yet | Sudha | not yet done | Vishal,Suchitra
E7 | Analytics and reporting | US7 | As a user,I want to view analytics in charts and graphs for better visualization. | Database connectivity and optimize search algorthim | Must have |  | Not yet | Suchitha | not yet done | Vishal
E8 | Real-time Data updates | US5 | As a user,I want the dashboard to upadte data automatically without manual refresh | Web socket | Should Have |  | not yet | Sudha,suchitha | not yet done | suchitra
E9 | Role-based dashboards | US9 | I want to manage different dashboard views for different user roles | database connectivity | Could Have |  | not yet | sudha | not yet done | suchitra
E10 | Notification and alerts | US10 | I want to receive notification on dashboard for important updates and alerts | push notification api | could have |  | not yet | sudha | not yet done | Vishal
E11 | Search and filter | US11 | I want to search for records/insights within the dashboard | searching algorithm | could have |  | not yet | suchitha | not yet done | vishal
E12 | UI/UX Design | US12 | As a user,I want a consistent color theme and typography so that the platform feels professional | CSS | Must Have |  | almost there | Jayanth | not yet done | Vishal,Suchitra
E13 | Visual Consistency and Branding | US13 | I want a visually appealing interface so that I can easily navigate the platform’s professionalism |  | Must Have |  | almost there | Jayanth | not yet done | Vishal,Suchitra
E14 | Error & Empty States | US14 | I want clear error and empty-state screens so I understand what went wrong and what action to take next. |  | Must Have |  | Not yet | Jayanth | not yet done | Vishal,Suchitra
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release | Target Date | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Session Transcription | transcription model, minimal and stable UI | done
v0.2 | 2025-11-22 | Doctor Notes + Review | Requires API upgrade | done
v0.3 | 2025-11-29 | seamless session documentation,UI/UX design | Speech-to-Text API | done
v0.4 | 2025-12-06 | AI-based Summarization | Requires transcript output | done
v0.5 | 2025-12-13 | Emotion & Keyword Detection | Backend model integration | done
v1.0 | 2025-12-20 | Analytics export-report generation | Encryption + DB setup | done
v1.1 | 2025-12-27 | Analytics Dashboard Enhancements | UI design system | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead